## 📖 Instructions
TOOL GUIDE — VALAR ATOMICS PROCUREMENT & ESTIMATING TOOL
SHEET | PURPOSE & INSTRUCTIONS
📊 Dashboard | High-level KPIs and phase budget summary. Phase budgets and actuals must be entered on this sheet (Budget and Actual Spend columns). Variance and % Complete calculate automatically.
📋 Contractor Register | Master list of all subcontractors by phase/scope. Enter contractor details, bid status, contract values. Retainage Held calculates automatically. Color codes: Green=Awarded, Yellow=Bid Received, Red=Cancelled.
⚖️ Bid Leveling | Use one tab per bid package. Enter bidder names in row 8, line-item prices in blue cells. Totals calculate automatically. Paste award recommendation at bottom.
📦 Procurement Tracker | Track all materials and equipment. Enter PO data, delivery dates, and status. Total PO Value calculates from Qty × Unit Price. Use Delivery Status dropdown. Red = Expedite Required.
🔄 Change Orders | Log all contract changes. Enter original contract value and CO amount; Revised Contract calculates automatically. Totals of Approved and Pending COs shown at top.
⚠️ Risk Register | Document procurement and construction risks. Enter Probability (1-5) and Impact (1-5); Risk Score and Level calculate automatically. Update Status as risks are mitigated.
✅ Prequalification | Track subcontractor and supplier prequalification status. Required before inviting companies to bid. Color codes: Green=Approved, Yellow=Expired, Red=Rejected.
👥 RACI Matrix | Defines who is Responsible, Accountable, Consulted, and Informed for each work package. Update role names in row 6 to match your actual team.
COLOR CODING KEY:
Blue text | User input / hardcoded values
Black text | Calculated formulas
Green background | Approved / Complete / Awarded
Yellow background | Pending / Warning / Bid Received
Red background | Critical / Cancelled / Expedite Required
Orange header | Risk / Watchlist items

## 📊 Dashboard
VALAR ATOMICS — CONSTRUCTION PROCUREMENT & ESTIMATING TOOL
Pilot Plant — Orangeville, Utah
TOTAL CONTRACT VALUE |  |  |  | TOTAL COMMITTED |  |  |  | TOTAL VARIANCE
0 |  |  |  | 0 |  |  |  | 0
PHASE BUDGET SUMMARY
Construction Phase |  | Budget ($) | Committed ($) |  | Actual Spend ($) | Variance ($) | % Complete |  | Status
01 – Site Preparation & Earthwork |  | 0 | 0 |  | 0 | 0 | 0% |  | —
02 – Civil & Foundations |  | 0 | 0 |  | 0 | 0 | 0% |  | —
03 – Structural Steel & Building Envelope |  | 0 | 0 |  | 0 | 0 | 0% |  | —
04 – Mechanical & Process Piping |  | 0 | 0 |  | 0 | 0 | 0% |  | —
05 – Electrical & Instrumentation |  | 0 | 0 |  | 0 | 0 | 0% |  | —
06 – Nuclear Island & Reactor Installation |  | 0 | 0 |  | 0 | 0 | 0% |  | —
07 – HVAC & Ventilation |  | 0 | 0 |  | 0 | 0 | 0% |  | —
08 – Fire Protection |  | 0 | 0 |  | 0 | 0 | 0% |  | —
09 – Fuel Fabrication Facility |  | 0 | 0 |  | 0 | 0 | 0% |  | —
10 – Commissioning & Startup |  | 0 | 0 |  | 0 | 0 | 0% |  | —
11 – Environmental & Regulatory |  | 0 | 0 |  | 0 | 0 | 0% |  | —
12 – Owner Costs & Contingency |  | 0 | 0 |  | 0 | 0 | 0% |  | —
TOTAL |  | 0 | 0 |  | 0 | 0 | 0%
⚠️ LONG-LEAD & RISK WATCHLIST (auto-pulled from Risk Register)
Item | Category | Owner | Required On-Site Date |  | Order Date | Lead Time (wks) | Status |  | Risk Level

## 📋 Contractor Register
CONTRACTOR REGISTER & BID LEVELING
Total Contract Value: | [18 empty] | 0
Total Committed: | [18 empty] | 0
Variance vs Budget: | [18 empty] | 0
Phase # | Construction Phase | Trade / Scope | Contractor Name | DBA / Trade Name | Contact Name | Phone | Email | Prequalified? | Insurance Verified? | License # | Bid Status | Bid Due Date | Contract Value ($) | Retainage % | Retainage Held ($) | Contract Type | Contract Date | NTP Date | Substantial Completion | Final Completion | Safety Rating | Notes / Qualifications | Internal Owner
01 | Site Prep & Earthwork | Earthwork & Grading | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | PM: TBD
01 | Site Prep & Earthwork | Demolition & Clearing | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | PM: TBD
01 | Site Prep & Earthwork | Erosion Control / SWPPP | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | EH&S Lead
02 | Civil & Foundations | Concrete / Foundations | [8 empty] | Bidding |  |  | 10% | 0 | Lump Sum | [6 empty] | Civil Engr
02 | Civil & Foundations | Geotechnical / Piling | [8 empty] | Bidding |  |  | 5% | 0 | Unit Price | [6 empty] | Civil Engr
02 | Civil & Foundations | Underground Utilities | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Civil Engr
02 | Civil & Foundations | Site Concrete & Paving | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Civil Engr
03 | Structural Steel | Structural Steel Fabrication | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Struct Engr
03 | Structural Steel | Steel Erection | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Struct Engr
03 | Structural Steel | Metal Decking & Joists | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Struct Engr
03 | Structural Steel | Roofing & Cladding | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Arch/PM
03 | Structural Steel | Doors, Windows & Glazing | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Arch/PM
04 | Mechanical & Piping | Process Piping Fabrication | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Mech Engr
04 | Mechanical & Piping | Piping Installation | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Mech Engr
04 | Mechanical & Piping | Insulation | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Mech Engr
04 | Mechanical & Piping | Pumps & Rotating Equipment | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Mech Engr
04 | Mechanical & Piping | Pressure Vessels & HX | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Mech Engr
05 | Electrical & I&C | Electrical Distribution | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Elec Engr
05 | Electrical & I&C | Cable Tray & Conduit | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Elec Engr
05 | Electrical & I&C | Motor Control Centers | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Elec Engr
05 | Electrical & I&C | Instrumentation & Controls | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | I&C Engr
05 | Electrical & I&C | DCS / SCADA Integration | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | I&C Engr
06 | Nuclear Island | Reactor Vessel Installation | [8 empty] | Bidding |  |  | 5% | 0 | Cost Plus | [6 empty] | Nuclear Engr
06 | Nuclear Island | Nuclear-Grade Piping | [8 empty] | Bidding |  |  | 5% | 0 | Cost Plus | [6 empty] | Nuclear Engr
06 | Nuclear Island | Shielding & Containment | [8 empty] | Bidding |  |  | 5% | 0 | Cost Plus | [6 empty] | Nuclear Engr
07 | HVAC & Ventilation | General HVAC | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | Mech Engr
07 | HVAC & Ventilation | Nuclear-Grade Ventilation / HEPA | [8 empty] | Bidding |  |  | 5% | 0 | Cost Plus | [6 empty] | Nuclear Engr
08 | Fire Protection | Sprinkler Systems | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | FP Engr
08 | Fire Protection | Fire Alarm & Detection | [8 empty] | Bidding |  |  | 5% | 0 | Lump Sum | [6 empty] | FP Engr
09 | Fuel Fabrication | Fuel Assembly Equipment | [8 empty] | Bidding |  |  | 5% | 0 | Cost Plus | [6 empty] | Nuclear Engr
09 | Fuel Fabrication | Gloveboxes & Hot Cells | [8 empty] | Bidding |  |  | 5% | 0 | Cost Plus | [6 empty] | Nuclear Engr
10 | Commissioning | Pre-Commissioning & Flushing | [8 empty] | Bidding |  |  | 5% | 0 | T&M | [6 empty] | Comm Mgr
10 | Commissioning | Cold/Hot Functional Testing | [8 empty] | Bidding |  |  | 5% | 0 | T&M | [6 empty] | Comm Mgr
11 | Environmental & Regulatory | Environmental Monitoring | [8 empty] | Bidding |  |  | 5% | 0 | Unit Price | [6 empty] | EH&S Lead
11 | Environmental & Regulatory | Waste Handling & Disposal | [8 empty] | Bidding |  |  | 5% | 0 | Unit Price | [6 empty] | EH&S Lead
12 | Owner Costs | Construction Management | [8 empty] | Bidding |  |  | 0% | 0 | Cost Plus | [6 empty] | Owner
12 | Owner Costs | Owner-Furnished Equipment | [11 empty] | 0% | 0 | [7 empty] | Procurement
12 | Owner Costs | Contingency | [11 empty] | 0% | 0 | [7 empty] | Dir Projects

## ⚖️ Bid Leveling
BID LEVELING & COST COMPARISON
INSTRUCTIONS: Enter scope/package name in B6, then enter bidder names and their line-item pricing. Green = Low Bid. Yellow = within 10% of low. Use for apples-to-apples comparison before award recommendation.
Bid Package: | [ Enter Package Name ] | [5 empty] | Bid Date:
Scope / Line Item | Bidder 1 — Enter Name |  |  | Bidder 2 — Enter Name |  |  | Bidder 3 — Enter Name |  |  | Bidder 4 — Enter Name |  |  | Bidder 5 — Enter Name |  |  | Bidder 6 — Enter Name
| Base Bid ($) | Alternates ($) | Total ($) | Base Bid ($) | Alternates ($) | Total ($) | Base Bid ($) | Alternates ($) | Total ($) | Base Bid ($) | Alternates ($) | Total ($) | Base Bid ($) | Alternates ($) | Total ($) | Base Bid ($) | Alternates ($) | Total ($)
Mobilization / Demobilization |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Bonds & Insurance |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
General Conditions |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Site Preparation |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Earthwork / Grading |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Foundations |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Structural |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Mechanical |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Electrical |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Piping |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Insulation |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Painting & Coatings |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Testing & Inspection |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Startup & Commissioning Support |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Spare Parts & Special Tools |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Alternate 1 – [Describe] |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Alternate 2 – [Describe] |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Sales Tax / Use Tax |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Escalation / Contingency Allowance |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
TOTAL BID | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AWARD RECOMMENDATION:

## 📦 Procurement Tracker
MATERIALS & EQUIPMENT PROCUREMENT TRACKER
Item # | Description | Phase | Category | Supplier / Vendor | Spec / Drawing Ref | Qty | Unit | Unit Price ($) | Total PO Value ($) | PO # | PO Issued Date | Promised Delivery | Required On-Site | Lead Time (wks) | Delivery Status | Inspection Req? | Internal Owner | Budget Line | Notes / Issues
001 | Reactor Pressure Vessel | 06 Nuclear Island | Long Lead | TBD | N-100 | 1 | EA |  | 0 |  |  |  |  | 52 | Not Ordered | Yes | Nuclear Engr | 06-001 | ⚠️ Critical Long Lead
002 | Main Transformer | 05 Electrical | Long Lead | TBD | E-200 | 1 | EA |  | 0 |  |  |  |  | 40 | Not Ordered | Yes | Elec Engr | 05-001 | ⚠️ Long Lead
003 | DCS / Control System | 05 Electrical | Long Lead | TBD | I-300 | 1 | LS |  | 0 |  |  |  |  | 36 | Not Ordered | Yes | I&C Engr | 05-002
004 | Emergency Diesel Generator | 05 Electrical | Long Lead | TBD | E-210 | 2 | EA |  | 0 |  |  |  |  | 30 | Not Ordered | Yes | Elec Engr | 05-003
005 | Heat Exchanger – Primary | 04 Mechanical | Engineered Equipment | TBD | M-101 | 3 | EA |  | 0 |  |  |  |  | 24 | Not Ordered | Yes | Mech Engr | 04-001
006 | Process Pumps – High Temp | 04 Mechanical | Engineered Equipment | TBD | M-110 | 6 | EA |  | 0 |  |  |  |  | 20 | Not Ordered | Yes | Mech Engr | 04-002
007 | Structural Steel Package | 03 Structural | Long Lead | TBD | S-100 | 1 | LS |  | 0 |  |  |  |  | 16 | Not Ordered | No | Struct Engr | 03-001
008 | Nuclear Grade Pipe (Various) | 04 Mechanical | Long Lead | TBD | M-200 | 1 | LS |  | 0 |  |  |  |  | 18 | Not Ordered | Yes | Mech Engr | 04-003
009 | Electrical Switchgear | 05 Electrical | Engineered Equipment | TBD | E-220 | 1 | LS |  | 0 |  |  |  |  | 20 | Not Ordered | Yes | Elec Engr | 05-004
010 | HEPA Filtration Units | 07 HVAC | Long Lead | TBD | H-100 | 12 | EA |  | 0 |  |  |  |  | 24 | Not Ordered | Yes | Nuclear Engr | 07-001 | Nuclear grade
011 | Concrete – Structural | 02 Civil | Bulk Material | TBD | C-100 |  | CY |  | 0 |  |  |  |  | 4 | Not Ordered | No | Civil Engr | 02-001
012 | Rebar – Structural | 02 Civil | Bulk Material | TBD | C-101 |  | Tons |  | 0 |  |  |  |  | 6 | Not Ordered | No | Civil Engr | 02-002
013 | Conduit & Cable Tray | 05 Electrical | Bulk Material | TBD | E-300 |  | LF |  | 0 |  |  |  |  | 8 | Not Ordered | No | Elec Engr | 05-005
014 | Instrumentation (General) | 05 Electrical | Engineered Equipment | TBD | I-400 | 1 | LS |  | 0 |  |  |  |  | 16 | Not Ordered | Yes | I&C Engr | 05-006
015 | Fire Suppression Equipment | 08 Fire | Engineered Equipment | TBD | FP-100 | 1 | LS |  | 0 |  |  |  |  | 12 | Not Ordered | No | FP Engr | 08-001

## 🔄 Change Orders
CHANGE ORDER & CONTRACT MODIFICATION LOG
Total Approved Change Orders: |  |  |  |  | 0
CO # | Contractor Name | Phase | Description of Change | Reason Code | Submitted Date | Decision Date | Status | Original Contract ($) | CO Amount ($) | Revised Contract ($) | Schedule Impact (days) | Approved By | Notes
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## ⚠️ Risk Register
PROCUREMENT & CONSTRUCTION RISK REGISTER
Risk ID | Phase | Risk Description | Category | Probability (1-5) | Impact (1-5) | Risk Score | Risk Level | Mitigation Action | Contingency Plan | Owner | Due Date | Status | Cost Exposure ($) | Schedule Exposure (days) | Notes
R-001 | 06 Nuclear Island | Reactor vessel delivery delay (52-wk lead) | Supply Chain | 4 | 5 | 20 | 🔴 Critical | Secure slot with 3 qualified vendors; issue LOI immediately | Identify alternate vessel design | Nuclear Engr |  | Open
R-002 | 05 Electrical | Main transformer lead time 40+ wks | Supply Chain | 3 | 4 | 12 | 🟠 High | Issue RFQ immediately; evaluate refurbished unit | Pre-identify temporary power solution | Elec Engr |  | Open
R-003 | 02 Civil | Unexpected geotechnical conditions at pilot site | Technical | 3 | 4 | 12 | 🟠 High | Complete full geotech investigation before bid issue | Carry contingency in foundations budget | Civil Engr |  | Open
R-004 | All | Skilled craft labor shortage in Utah | Supply Chain | 4 | 3 | 12 | 🟠 High | Early engagement with trade unions; consider traveling crews | Budget craft labor premium | PM |  | Open
R-005 | 06 Nuclear Island | NRC licensing delay | Regulatory/NRC | 3 | 5 | 15 | 🔴 Critical | Maintain proactive NRC engagement; pre-application meetings | Build schedule float into nuclear scope | Nuclear Engr |  | Open
R-006 | 04 Mechanical | Nuclear-grade pipe certification lead times | Supply Chain | 3 | 3 | 9 | 🟠 High | Identify qualified mills early; consider pre-buy | Evaluate acceptable alternates with engineering | Mech Engr |  | Open
R-007 | All | Single-source subcontractor failure | Subcontractor Performance | 2 | 4 | 8 | 🟡 Medium | Qualify 2+ contractors per critical scope | Maintain backup vendor list | Dir Projects |  | Open
R-008 | 10 Commissioning | Startup complexity exceeds schedule | Schedule | 3 | 4 | 12 | 🟠 High | Develop detailed commissioning plan 6 months early | Add schedule contingency buffer | Comm Mgr |  | Open

## ✅ Prequalification
SUBCONTRACTOR & SUPPLIER PREQUALIFICATION LOG
Company Name | Trade / Scope | Contact | Phone | Email | DUNS/EIN | Years in Business | Annual Revenue ($M) | EMR (Safety Rate) | OSHA Recordable Rate | Bonding Capacity ($M) | Insurance – GL | Insurance – WC | Nuclear-Grade Certified? | References (3 req) | Prequalified? | Approved Scopes | Expiry Date | Notes

## 👥 RACI Matrix
CONSTRUCTION RESPONSIBILITY MATRIX (RACI)
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Activity / Work Package | Dir Projects & Procurement | Construction Mgr | Nuclear Engr | Civil/Struct Engr | Mech Engr | Elec/I&C Engr | EH&S Lead | Finance/Cost Ctrl | QA/QC Mgr | Field Superintendent
PROCUREMENT
Subcontractor Sourcing & Vetting | A/R | C | C | C | C | C | I | I | I | I
Bid Package Preparation | A/R | C | C | C | C | C | I | I | I | C
Bid Evaluation & Leveling | A/R | C | C | C | C | C | C | I | I | I
Contract Negotiation & Award | A/R | C | I | I | I | I | I | C | I | I
Long-Lead Equipment Ordering | A/R | C | A | C | C | C | I | C | I | I
Material Delivery Coordination | R | A | I | C | C | C | I | I | I | A
Change Order Management | A/R | C | C | C | C | C | I | C | I | I
CONSTRUCTION
Site Preparation & Earthwork | C | A | I | R | I | I | C | I | C | R
Civil & Foundations | C | A | I | R | I | I | C | I | C | R
Structural Steel | C | A | I | R | I | I | C | I | C | R
Mechanical & Piping | C | A | C | C | R | I | C | I | C | R
Electrical & I&C | C | A | C | I | I | R | C | I | C | R
Nuclear Island Installation | C | A | R | C | C | C | C | I | R | R
HVAC & Ventilation | C | A | C | C | R | I | C | I | C | R
Fire Protection | C | A | I | C | C | C | C | I | C | R
CONTROLS & COMPLIANCE
Budget & Cost Control | A | C | I | I | I | I | I | R | I | I
Schedule Management | C | R | C | C | C | C | I | C | I | A
Safety Program | C | C | I | I | I | I | R | I | C | A
Quality Assurance | C | C | C | C | C | C | I | I | R | A
NRC/Regulatory Compliance | C | C | R | I | I | I | C | I | C | I
Subcontractor Performance Mgmt | A/R | R | I | I | I | I | C | I | C | C