## How to Use
CONTRACTOR REGISTER — HOW TO USE
Topic | Detail
PURPOSE | This register covers all 12 WBS construction phases for the Ward 250 HTGR pilot plant at USREL, Orangeville, Utah. Two tabs separate local Utah contractors from national firms. Use both: Utah for conventional scope, national for all nuclear-grade and safety-class work.
Utah Local Tab | Civil, earthwork, conventional structural steel, BOP electrical, HVAC (non-nuclear), and fire protection. These firms can price and mobilize within 150–200 miles. Do NOT assign nuclear island, safety-class I&C, or ASME Sec III piping to local Utah firms without verification of N-stamp.
National Tab | All nuclear-grade scope: reactor installation, N-stamp piping, RPS, nuclear I&C, NIAC, confinement HVAC, radwaste, fuel handling, PSAR/licensing. These firms must mobilize and will add a field cost premium (~15–25%) — budget accordingly.
CRITICAL PATH — Send RFQs FIRST | BWXT (nuclear install) ¦ Curtiss-Wright (RPS+I&C) ¦ Bureau Veritas (NIAC) ¦ EnergySolutions UT (radwaste) ¦ Scientech/CW (QA — Idaho Falls). These 5 have the longest lead times for mobilization, qualification, and contracting. Send LOI/RFQ before any other national firm.
ORANGE ROWS | Highlighted orange = critical path or safety-class scope. These require enhanced prequalification, QA audit, and early RFQ issue. Do not treat as standard commodity procurement.
GREEN CELLS (Nuclear/N-Stamp columns) | Green = confirmed Yes for nuclear or DOE experience. Yellow/amber = Partial. These should be prioritized in your bid slate for nuclear-scope packages.
DROPDOWN FIELDS | Prequalified? ¦ Nuclear Exp? ¦ N-Stamp? ¦ Bid Received? ¦ Contract Award — all use dropdowns. Click the cell to see options. Update these as you work through the bid process.
HOW TO SEND RFQ | 1. Mark 'RFQ Sent Date'. 2. Track 'Response Due Date' (suggest 3 weeks for conventional, 4–5 weeks for nuclear). 3. Update 'Bid Received?' when response arrives. 4. Transfer to Bid Leveling tab in the Procurement Tool for apples-to-apples comparison.
PHONE NUMBERS NOTE | Some phone/email fields show placeholders. Utah firms: verify current numbers via their website or Utah DOPL license lookup. National firms: numbers shown are HQ — request nuclear division direct line on first call.
ADDING CONTRACTORS | Insert rows within the appropriate WBS section. Copy formatting from the row above. Match the WBS # to the section banner to keep phases organized.
CONNECTING TO PROCUREMENT TOOL | This register feeds directly into the Contractor Register tab of the Ward 250 Procurement & Estimating Tool. When a contractor is Awarded, copy the company name, scope, and contract value over to that tool's master register.

## Utah Local Contractors
WARD 250 HTGR PILOT PLANT — 🏔️ UTAH LOCAL CONTRACTORS
USREL, Orangeville UT ¦ 100–250 kWt TRISO HTGR ¦ Use dropdown for status fields ¦ Highlighted rows = CRITICAL PRIORITY
WBS Phase # | Construction Phase / Scope | Trade / Scope of Work | Company Name | City / State | Distance to Site (mi) | Website | Primary Contact | Phone | Email | Nuclear / DOE Experience? | N-Stamp / NQA-1 Certified? | Prequalified? | RFQ Sent Date | Response Due Date | Bid Received? | Contract Award | Est. Contract Value ($) | Notes / Priority
WBS 01 — SITE PREP & EARTHWORK
01 | Site Prep & Earthwork | Earthwork, Grading & Excavation | Wollam Construction | Salt Lake City, UT | 180 | wollamconstruction.com | Estimating Dept | (801) 973-9600 | bids@wollamconstruction.com | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | 35+ yrs heavy civil/industrial UT. Self-perform earthwork, site improvements, underground utilities. Strong Intermountain West presence.
01 | Site Prep & Earthwork | Earthwork, Grading & Excavation | Gerber Construction | Salt Lake City, UT | 180 | gerberconstruction.com | Estimating | (801) 972-2500 | info@gerberconstruction.com | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | 50+ yr Utah heavy civil. $1B+ completed. Earthwork, concrete, steel fab in-house. Strong rural UT experience.
01 | Site Prep & Earthwork | Earthwork, Grading & Excavation | WW Clyde & Co. | Springville, UT | 140 | wwclyde.net | Business Development | (801) 489-3941 | info@wwclyde.net | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Utah institution — grading, earthwork, concrete flatwork, underground drainage. Rural project experience.
01 | Site Prep & Earthwork | Erosion Control / SWPPP | Enviro Worx | Salt Lake City, UT | 180 |  | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Local erosion control and SWPPP specialist. Verify UT license. Solicit from AGC-Utah member list.
WBS 02 — CIVIL & FOUNDATIONS
02 | Civil & Foundations | Concrete Foundations & Flatwork | Messerly Concrete | Salt Lake City, UT | 180 | messerlyconcrete.com | Estimating | (385) 202-7777 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Industrial/commercial concrete specialist UT. Tilt-up, ultra-flat, seismic-resistant. Review for heavy foundations.
02 | Civil & Foundations | Concrete Foundations & Flatwork | Gerber Construction | Salt Lake City, UT | 180 | gerberconstruction.com | Estimating | (801) 972-2500 | info@gerberconstruction.com | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | In-house concrete capability combined with earthwork. Turnkey civil subcontract potential.
02 | Civil & Foundations | Underground Utilities | Wollam Construction | Salt Lake City, UT | 180 | wollamconstruction.com | Estimating | (801) 973-9600 | bids@wollamconstruction.com | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Underground utilities, storm drain, sanitary — self-perform with earthwork package. Efficiency in combining scopes.
02 | Civil & Foundations | Geotechnical Investigation | Terracon Consultants (UT Office) | Salt Lake City, UT | 180 | terracon.com | SLC Office | (801) 466-4384 | slc@terracon.com | Yes | No | Pending Submission |  |  | Not Yet Sent | Pending |  | National firm with UT office. DOE/nuclear site geotech experience. Phase I/II, seismic analysis, soil borings.
WBS 03 — STRUCTURAL STEEL & BUILDING ENVELOPE
03 | Structural Steel & Building Envelope | Structural Steel Fabrication & Erection | Utah Steel | Salt Lake City, UT | 180 | utahsteel.com | Estimating | (801) 000-0000 | estimating@utahsteel.com | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Utah-based full scope structural fab+erection. Amazon, aircraft hangars, large industrials. Confirm seismic Cat I capability.
03 | Structural Steel & Building Envelope | Structural Steel Fabrication & Erection | HA Fab | Logan, UT | 220 |  | Estimating | (435) 750-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Utah structural fab/erection. 30,000 SF fabrication shop. Ships 250 tons/month. Review for nuclear-adjacent work history.
03 | Structural Steel & Building Envelope | Structural Steel Fabrication & Erection | Excell Steel Fabrication | Salt Lake City, UT | 180 | excellsteelfab.com | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Utah fab+erection specialist. One-stop structural steel. Confirm AWS D1.1 certified welders on staff.
03 | Structural Steel & Building Envelope | Pre-Engineered Metal Building | Advanced Steel Building Systems | Salt Lake City, UT | 180 | advancedsteelbuildings.com | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | 80+ yr combined exp. Authorized Nucor/Metallic dealer. Suitable for admin & auxiliary building envelope.
03 | Structural Steel & Building Envelope | Roofing & Metal Cladding | B Logic Construction LLC | Centerville, UT | 200 |  | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Commercial/industrial/government. Steel siding, PEMB erection, metal roofing. AGC/ABC UT member. Safety awards.
WBS 04 — NUCLEAR ISLAND & REACTOR SYSTEM
04 | Nuclear Island & Reactor System | Nuclear Mechanical Installation (N-stamp welding, rigging) | JB Henderson Construction | Salt Lake City, UT | 180 | jbhenderson.com | Nuclear Division | (801) 000-0000 |  | Yes | Partial | Pending Submission |  |  | Not Yet Sent | Pending |  | DOE Order 414.1D + NQA-1 approved supplier. ASME U/S/R stamps. Process piping, mechanical install. Best local candidate for nuclear-adjacent scope.
WBS 05 — MECHANICAL & PROCESS SYSTEMS
05 | Mechanical & Process Systems | Process Piping & Mechanical Installation | JB Henderson Construction | Salt Lake City, UT | 180 | jbhenderson.com | Estimating | (801) 000-0000 |  | Yes | Partial | Pending Submission |  |  | Not Yet Sent | Pending |  | NQA-1 capable. ASME certified. Process piping, mechanical installation, fabrication. Preferred local candidate for balance-of-plant piping.
05 | Mechanical & Process Systems | Process Piping & Mechanical Installation | KHI Mechanical | Salt Lake City, UT | 180 | khimechanical.net | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | UA Local 140 Pipefitters affiliated. Commercial/industrial HVAC and process piping. Confirm industrial process capability.
05 | Mechanical & Process Systems | HVAC & Ventilation (General) | Rocky Mountain Mechanical (RMM) | South Salt Lake, UT | 175 | rockymtnmech.com | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Leading UT commercial HVAC, plumbing, controls. Multi-million dollar industrial projects. Review for confinement HVAC sub-scope.
05 | Mechanical & Process Systems | HVAC & Ventilation (General) | Commercial Mechanical (CMSS) | Salt Lake City, UT | 180 | cmssutah.com | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | 50+ yr SLC mechanical contractor. Lab, data center, military, industrial HVAC. Projects throughout Western US.
05 | Mechanical & Process Systems | HVAC & Ventilation (General) | Service Mechanical Controls (SMC) | Salt Lake City, UT | 180 | smcutah.com | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | 38+ yr industrial HVAC in UT. Steam, hydronic, process heating, refrigeration. Local 24/7 service capability useful for startup.
WBS 06 — ELECTRICAL & I&C
06 | Electrical & I&C | Electrical Distribution & Installation | Cache Valley Electric (CVE) | Logan, UT | 220 | cve.com | Estimating | (435) 752-3900 |  | Yes | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Largest UT electrical contractor. 2,300 employees. Heavy industrial, mission critical, DOE facility experience. Completed projects in nearly every US state.
06 | Electrical & I&C | Electrical Distribution & Installation | Double D Electrical & Instrumentation | Salt Lake City, UT | 180 | doubledei.com | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | 20+ yr industrial E&I in UT. DCS, PLC, SCADA, loop checks. Refineries, utilities, pharma. Strong I&C capability for BOP controls.
06 | Electrical & I&C | Instrumentation & Controls (DCS/PLC) | Winward Electrical Services | Salt Lake City, UT | 180 | winwardelectric.com | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Nuclear SCADA experience noted on website. Coriolis calibration to EPRI standards. DCS/PLC installation, loop checks, commissioning.
06 | Electrical & I&C | Instrumentation & Controls (DCS/PLC) | AJC Electric | Salt Lake City, UT | 180 | ajc-electric.com | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | 50+ yr UT E&C. Custom control panels, industrial automation, instrumentation. Commercial and industrial. Confirm large project capacity.
WBS 07 — HVAC & VENTILATION
07 | HVAC & Ventilation | HVAC — Admin & Auxiliary Buildings | Rocky Mountain Mechanical (RMM) | South Salt Lake, UT | 175 | rockymtnmech.com | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | See entry under 05 — dual-scope potential. RFQ for conventional HVAC only; nuclear confinement HVAC requires national firm.
WBS 08 — FIRE PROTECTION
08 | Fire Protection | Fire Suppression & Alarm | Delta Fire Systems | Salt Lake City, UT | 180 | deltafire.com | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Founded 1963. Largest intermountain fire protection firm. Design, install, service for commercial, industrial, and government. Confirm App R analysis capability.
08 | Fire Protection | Fire Suppression & Alarm | Quality Fire Protection | Salt Lake City, UT | 180 |  | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | UT-based since 1985. Full-service design/install on Wasatch Front. Review for industrial and government project history.
08 | Fire Protection | Fire Suppression & Alarm | TST Fire Protection | Salt Lake City, UT | 180 |  | Estimating | (801) 000-0000 |  | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | 30+ yr UT sprinkler specialist. ESFR, foam systems, clean agent suppression. Confirm 10CFR50 App R familiarity.
WBS 09 — ENVIRONMENTAL & REGULATORY
09 | Environmental & Regulatory | Environmental Monitoring & SWPPP | Terracon Consultants (UT Office) | Salt Lake City, UT | 180 | terracon.com | SLC Office | (801) 466-4384 | slc@terracon.com | Yes | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Also listed in 02. Environmental assessment, site characterization, monitoring during construction. DOE/nuclear site history.
WBS 10 — OWNER SUPPORT / CM
10 | Owner Support / CM | Construction Management Support | Wollam Construction | Salt Lake City, UT | 180 | wollamconstruction.com | Business Dev | (801) 973-9600 | bids@wollamconstruction.com | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Self-perform GC capability across civil, structural, mechanical. Could serve as local GC for conventional scope. Dual-hat option.
10 | Owner Support / CM | Temporary Facilities & Site Support | WW Clyde & Co. | Springville, UT | 140 | wwclyde.net | Business Dev | (801) 489-3941 | info@wwclyde.net | No | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Rural UT presence. Temporary roads, laydown yards, access. Potentially useful for early site mobilization support.
⚠️ NOTE: Most Utah contractors do NOT hold N-stamps or NQA-1 certification. Use for conventional civil, structural, electrical, and mechanical BOP scope ONLY. Nuclear Island and safety-class I&C must come from national firms on the next tab.

## National Contractors
WARD 250 HTGR PILOT PLANT — 🌐 NATIONAL CONTRACTORS
USREL, Orangeville UT ¦ 100–250 kWt TRISO HTGR ¦ Use dropdown for status fields ¦ Highlighted rows = CRITICAL PRIORITY
WBS Phase # | Construction Phase / Scope | Trade / Scope of Work | Company Name | City / State | Distance to Site (mi) | Website | Primary Contact | Phone | Email | Nuclear / DOE Experience? | N-Stamp / NQA-1 Certified? | Prequalified? | RFQ Sent Date | Response Due Date | Bid Received? | Contract Award | Est. Contract Value ($) | Notes / Priority
WBS 01-02 — SITE PREP, CIVIL & FOUNDATIONS
01-02 | Site Prep, Civil & Foundations | Nuclear-Grade Civil / Heavy Foundations | PCL Construction (Nuclear Division) | Denver, CO (mobilize) | 350 | pcl.com | Nuclear Division | (303) 365-6464 | nuclear@pcl.com | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | NA, NS, NPT N-stamp certified. Only Western Canadian/Western US contractor with 3 nuclear N-stamps. DOE construction experience. Will mobilize nationally.
01-02 | Site Prep, Civil & Foundations | Heavy Civil / Earthwork | Kiewit Corporation | Omaha, NE (mobilize) | ~1200 | kiewit.com | Rocky Mountain District | (720) 000-0000 |  | Yes | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Top-5 US contractor. DOE, Hanford, INL experience. Self-perform earthwork, civil, concrete, mechanical. Large mobilization capability. Overkill but competitive on lump sum.
WBS 03 — STRUCTURAL STEEL & BUILDING ENVELOPE
03 | Structural Steel & Building Envelope | Seismic Cat I Structural Steel | Banker Steel | Lynchburg, VA (fabricate, mobilize erection) | ~2000 | bankersteel.com | Estimating | (434) 582-3200 | estimating@bankersteel.com | Yes | No | Pending Submission |  |  | Not Yet Sent | Pending |  | AISC-certified structural fab. Nuclear plant structural steel experience (V.C. Summer, Vogtle). Will ship nationwide + mobilize erection crew.
03 | Structural Steel & Building Envelope | Seismic Cat I Structural Steel | Comprehensive Shielding Solutions (CSS) | Oak Ridge, TN (mobilize) | ~1800 |  | Estimating | (865) 000-0000 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | Specialized in radiation shielding design and installation. Nuclear-grade concrete, lead, and steel shielding. Unique scope for reactor building.
WBS 04 — NUCLEAR ISLAND & REACTOR SYSTEM
04 | Nuclear Island & Reactor System | N-Stamp Nuclear Component Installation | BWXT (BWX Technologies) | Lynchburg, VA (mobilize) | ~2000 | bwxt.com | Government Programs | (434) 522-6100 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | Premier US nuclear manufacturer. TRISO fuel capability. N-stamp (N, NA, NPT, NV). DOE, DoD, national lab experience. Critical path RFQ — send immediately.
04 | Nuclear Island & Reactor System | N-Stamp Nuclear Component Installation | Curtiss-Wright Nuclear | Charlotte, NC (mobilize) | ~2100 | curtisswright.com | Nuclear Division | (704) 869-4600 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | N-stamp certified. Nuclear valves, pumps, instrumentation, installation services. DOE and NRC-licensed plant experience. Will mobilize field team.
04 | Nuclear Island & Reactor System | Nuclear Piping Fabrication & Installation | CB&I (McDermott) | The Woodlands, TX (mobilize) | ~1600 | mcdermott.com | Nuclear Division | (832) 513-1000 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | Legacy nuclear EPC contractor. N-stamp piping fab and installation. AP1000 experience. Large mobilization capability. Critical for ASME Sec III piping.
04 | Nuclear Island & Reactor System | Nuclear Mechanical / Reactor Installation | Zachry Nuclear | San Antonio, TX (mobilize) | ~1500 | zachrynuclear.com | President's Office | (210) 588-5000 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | 50 yr nuclear experience. Engineering + construction + SMR design services. Non-LWR advanced reactor experience. Will mobilize field crews nationally.
04 | Nuclear Island & Reactor System | Nuclear Inspection Agency (NIAC) | Bureau Veritas Nuclear | Houston, TX (mobilize) | ~1600 | bureauveritas.com | Nuclear Division | (832) 000-0000 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | ASME-authorized inspection agency. Nuclear Inspector Supervisors for all N-stamp work. Required third-party for ASME Sec III scope. Critical procurement.
04 | Nuclear Island & Reactor System | Nuclear Inspection Agency (NIAC) — Alt | Applus+ RTD / Nuclear | Houston, TX (mobilize) | ~1600 | applusrtd.com | Nuclear Services | (713) 000-0000 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | NDE and nuclear inspection services. ASME authorized. NQA-1 quality programs. Alternative to Bureau Veritas for NIAC role.
WBS 05 — MECHANICAL & PROCESS SYSTEMS
05 | Mechanical & Process Systems | Helium Systems / High-Temp Process Piping | Graham Corporation | Batavia, NY (mobilize) | ~2200 | grahamcorp.com | Energy Division | (585) 343-2216 |  | Yes | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Nuclear and defense heat exchangers, vacuum systems. HTGR-relevant helium/high-temp process equipment. ASME certified. Niche but critical scope.
05 | Mechanical & Process Systems | Industrial Mechanical & Piping (BOP) | Performance Contractors | Baton Rouge, LA (mobilize) | ~1800 | performance-contractors.com | E&I Division | (225) 753-5765 |  | Yes | No | Pending Submission |  |  | Not Yet Sent | Pending |  | 500+ E&I craftsmen. Multi-state industrial mechanical, E&I. Energy, chemical, power plant experience. Strong mobilization track record.
05 | Mechanical & Process Systems | Industrial Mechanical & Process Piping | Turner Industries Group | Baton Rouge, LA (mobilize) | ~1800 | turnerindustries.com | Estimating | (225) 922-5050 |  | Yes | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Large industrial mechanical contractor. Refineries, power plants, chemical plants. E&I, mechanical, insulation self-perform. Will mobilize.
WBS 06 — ELECTRICAL & I&C
06 | Electrical & I&C | Safety-Class Reactor Protection System (RPS) | Curtiss-Wright Nuclear (Controls Div) | Charlotte, NC (mobilize) | ~2100 | curtisswright.com | I&C Division | (704) 869-4600 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | IEEE 603 qualified RPS, safety-class I&C design and installation. Nuclear-qualified sensors, trip logic. Critical path. Early engagement required.
06 | Electrical & I&C | Safety-Class Reactor Protection System (RPS) | Rolls-Royce Nuclear (I&C) | Lynchburg, VA (mobilize) | ~2000 | rolls-royce.com | Nuclear I&C | (434) 522-0000 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | Nuclear I&C systems, RPS, post-accident monitoring. DOE and commercial nuclear. Evaluate for RPS scope.
06 | Electrical & I&C | Electrical Distribution (Heavy Industrial) | Egan Company | Minneapolis, MN (mobilize) | ~1100 | eganco.com | Industrial Division | (763) 544-4131 |  | Yes | No | Pending Submission |  |  | Not Yet Sent | Pending |  | National industrial electrical contractor. Power plants, industrial facilities. Will mobilize western US. Review for MCC, switchgear, cable install.
06 | Electrical & I&C | Radiation Monitoring System | Mirion Technologies | Atlanta, GA (mobilize) | ~2000 | mirion.com | Nuclear Systems | (770) 859-3300 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | Market leader in nuclear radiation detection and monitoring. Area monitors, stack monitors, CAMS. DOE and commercial nuclear supply chain.
06 | Electrical & I&C | Nuclear Instrumentation (In-Core, Ex-Vessel) | Reuter-Stokes (Baker Hughes) | Twinsburg, OH (supply) | ~1800 | bakerhughes.com | Nuclear Instruments | (330) 425-3755 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | Leading supplier of nuclear in-core detectors, ex-vessel flux monitors. Neutron flux detectors for HTGR test reactors. Long lead — order early.
WBS 07 — HVAC & VENTILATION
07 | HVAC & Ventilation | Nuclear-Grade HVAC / Confinement Ventilation | Aecom (Nuclear Division) | Los Angeles, CA (mobilize) | ~750 | aecom.com | Nuclear Division | (213) 593-8000 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | Global EPC with nuclear HVAC design/build. Confinement ventilation, HEPA filtration systems, DOE facility experience. Can provide engineering + procurement + installation.
07 | HVAC & Ventilation | Nuclear-Grade HVAC / Confinement Ventilation | Camfil APC (HEPA Systems) | Jonesboro, AR (supply) | ~1400 | camfil.com | Nuclear Products | (870) 933-8048 |  | Yes | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Premier HEPA filtration manufacturer for nuclear and DOE. Nuclear-grade HEPA housings and filters. Confinement exhaust filtration supply.
WBS 08 — FIRE PROTECTION
08 | Fire Protection | 10CFR50 App R / Nuclear Fire Analysis | Jensen Hughes | Baltimore, MD (mobilize) | ~2000 | jensenhughes.com | Nuclear Fire Safety | (410) 737-8677 |  | Yes | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Leading nuclear fire protection engineering firm. 10CFR50 Appendix R analysis, fire hazard analysis, barrier evaluation. Engineering-only scope.
08 | Fire Protection | Fire Suppression Installation (Nuclear Facility) | Puffer-Sweiven / Emerson | Houston, TX (mobilize) | ~1600 | puffersweiven.com | Fire Safety | (713) 937-1700 |  | Yes | No | Pending Submission |  |  | Not Yet Sent | Pending |  | Nuclear plant fire protection installation experience. Pre-action and CO2 systems in safety-class electrical rooms. Will mobilize.
WBS 09 — FUEL HANDLING & WASTE MANAGEMENT
09 | Fuel Handling & Waste Management | Radwaste Processing & Fuel Handling Systems | Holtec International | Camden, NJ (mobilize) | ~2300 | holtecinternational.com | Decon & Decommission Div | (856) 797-0900 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | Premier nuclear dry storage, radwaste, fuel handling. Cask design, fuel transfer equipment. ASME N-stamp. Very relevant to Ward 250 fuel handling scope.
09 | Fuel Handling & Waste Management | Radwaste Processing & Fuel Handling Systems | EnergySolutions | Salt Lake City, UT | 180 | energysolutions.com | UT HQ | (801) 649-2000 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | UT-BASED nuclear company. Radwaste management, decommissioning, DOE site work. Local AND nuclear-qualified. High priority contact for radwaste scope.
WBS 10 — COMMISSIONING & STARTUP
10 | Commissioning & Startup | Startup Engineering & Testing | Enercon Services | Kennesaw, GA (mobilize) | ~1800 | enercon.com | Nuclear Division | (770) 919-1930 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | Advanced nuclear SMR engineering partner. Holtec SMR-300 CPA support. DOE facility startup experience. Engineering + licensing + startup services.
10 | Commissioning & Startup | Startup Engineering & Testing | GSE Systems (Curtiss-Wright) | Sykesville, MD (mobilize) | ~2100 | gses.com | Nuclear Division | (410) 970-7800 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | Nuclear plant simulation, operator training, startup testing support. Non-LWR experience. Evaluate for Ward 250 low-power startup program support.
WBS 11 — ENVIRONMENTAL & REGULATORY
11 | Environmental & Regulatory | NEPA / Environmental Assessment | Tetra Tech | Pasadena, CA (mobilize) | ~750 | tetratech.com | Nuclear & Environment Div | (626) 470-2844 |  | Yes | No | Pending Submission |  |  | Not Yet Sent | Pending |  | National environmental and nuclear consulting. NEPA EA/EIS, cultural resources, DOE site environmental assessments. Will assign resident team.
11 | Environmental & Regulatory | QA Program (10CFR50 App B / NQA-1) | Scientech (a Curtiss-Wright Co.) | Idaho Falls, ID (mobilize) | ~280 |  | Nuclear QA | (208) 528-6166 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | Nuclear QA program development, 10CFR50 App B compliance, NQA-1 auditing. Idaho Falls — nearest nuclear QA resource to Orangeville. HIGH PRIORITY.
11 | Environmental & Regulatory | Safety Analysis / PSAR | ENERCON Services | Kennesaw, GA (mobilize) | ~1800 | enercon.com | Licensing Division | (770) 919-1930 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | PSAR/SAR preparation for SMR and advanced reactors. DOE authorization application support. Engineering + licensing integrated team.
11 | Environmental & Regulatory | Radiation Protection Program | Radiation Protection Solutions (RPS) | Idaho Falls, ID (mobilize) | ~280 |  | HP Manager | (208) 000-0000 |  | Yes | No | Pending Submission |  |  | Not Yet Sent | Pending |  | HP staffing, RP program development, ALARA implementation for nuclear construction. Idaho Falls proximity to USREL advantageous.
WBS 12 — OWNER COSTS / EPC
12 | Owner Costs / EPC | Overall EPC / Construction Management | Fluor Corporation (Nuclear) | Irving, TX (mobilize) | ~1500 | fluor.com | Nuclear Division | (469) 398-7000 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | N-stamp certified EPC. AP1000, MOX, DOE Hanford experience. Could take EPC role for conventional+nuclear scope. Evaluate as prime contractor.
12 | Owner Costs / EPC | Overall EPC / Construction Management | Aecom (Nuclear) | Los Angeles, CA (mobilize) | ~750 | aecom.com | Nuclear Division | (213) 593-8000 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | West-Coast nuclear EPC. DOE, INL, NRC experience. Proximity advantage over eastern EPC firms. Evaluate for EPCM role.
12 | Owner Costs / EPC | Nuclear QA / Inspection | NQA Group (NIAC) | Burlington, MA (mobilize) | ~2400 |  | NIAC Manager | (781) 000-0000 |  | Yes | Yes | Pending Submission |  |  | Not Yet Sent | Pending |  | ASME-authorized inspection agency (NIAC). Nuclear Inspector Supervisors for N-stamp work. Essential for all ASME Sec III scope.
🚨 CRITICAL PATH CONTACTS: BWXT (nuclear install), Curtiss-Wright (RPS & I&C), Bureau Veritas (NIAC), EnergySolutions (radwaste — UT-based), Scientech/CW (QA — Idaho Falls). Send RFQ/LOI to these 5 BEFORE any other national contractor.